Nuthurst Parish Plan: Interim Progress Report: January to June 2017

| No. | Project | Output | Comment | Any Problems? | Outstanding Action |
| --- | --- | --- | --- | --- | --- |
| 1 | Monitor planning applications to ensure compliance with the Neighbourhood Plan and the Parish Design Statement Cllrs Court, Hydes | 1). Coombe Cott, DC/17/0302 – objected strongly – not compliant NP/PDS - refused. DC/17/1195 – objected strongly – not compliant NP/PDS - not determined. 2) Dun Horse Pub DC/16/2382, objected strongly – not compliant with NP/PDS - not determined. DC/17/0301 and several amendments -- objected strongly to all – not complaint with NP/PDS– not determined. 3) Opp Dun Horse DC/16/1753– supported amended application for NP site –approved. 4) Swallowfield Nursery DC/14/2755, – NP site – objected - not compliant with NP – not determined. DC/17/1158 – objected as not compliant with NP –not determined. | 1) All planning applications are very closely scrutinised and monitored –there is more need to do this than previously 2) Continuing threats to NP/PDS - Church Road - Dun Horse Pub - Swallowfield Nursery - 22 Gagglewood 3) Help appreciated from MHAG members commenting on planning applications 4) Cllrs Court, Hydes and Bradnum had meeting with HDC planning officers on 22 June regarding adjacent problems 1) and 2 and officers intention to controversially approve Church Road – DC/17/0815. Meeting made good progress but need to see if HDC deliver | 1) At times a lack of support from some HDC Officers and officers not using the NP/PDS 2) Difficulty obtaining answers from HDC to important letters and queries 3) Misleading and missing information on developers planning applications 4) Monitoring planning applications is proving very time consuming | Ongoing very close scrutiny, commenting and monitoring |

| No. | Project | Output | Comment | Any Problems? | Outstanding Action |
| --- | --- | --- | --- | --- | --- |
|  |  | 5) Church Road, DC/17/0815 - Not in NP, objected strongly as not compliant with NP/PDS - not determined. 6) 22 Gagglewood, DC/17/1139 – objected strongly – not compliant with NP/PDS – not determined. 7) Monks Gate land parcel, DC/17/0667 – NP site – supported with provisos – recommended for approval – to HDC Committee 4 July – Cllr Hydes to speak in support with provisos 8) Cllr Hydes spoke at 2 HDC Committee meetings against DC/16/2062, Millers Mead –successful, and DC/16/2727, Sedgwick Park - unsuccessful |  |  |  |
| 2 | To raise public awareness of the Parish Design Statement Cllr Hydes | 1) On NPC and NP websites 2) On 8 Parish notice boards 3) Article submitted for July LINK | On target | No | Publicise from time to time |

| No. | Project | Output | Comment | Any Problems? | Outstanding Action |
| --- | --- | --- | --- | --- | --- |
| 3 | To up-date the Parish Council’s website so that it can be better used to convey information to, and receive information from, the public Cllr Nelson, Clerk | 1) New website complete and live 2) Advertised on 8 Parish notice boards w/c 19 June 3) to be advertised in the July LINK | Completed | No | None |
| 4 | To monitor the frequency of the events listed under project 3(i) of the three year plan Cllr Nelson, Clerk |  | Cllr Nelson has suggested residents should have access to information on what has been reported, repaired and actioned |  | On-going. Cllr Nelson and Clerk will start to monitor information when residents input it to the website. Clerk to include on September agenda. |
| 5 | To monitor the facilities listed under project 3(ii) of the three year plan Cllr Nelson, Clerk | 1) Facilities included on the new website 2) Included in the Resilience Plan |  |  | Clerk will continue to monitor any changes in facilities and contact details |

| No. | Project | Output | Comment | Any Problems? | Outstanding Action |  |
| --- | --- | --- | --- | --- | --- | --- |
| 6 | To reduce traffic speeding and improve road safety in the Parish Cllrs Court, Mercer/Nelson, Turner, Clerk | 1) Village gateways have been identified, approved for purchase, and in the process of being purchased and installed. 2) Consultation with parents about 20mph limit at St Andrews School in progress 3) Presentation by Parish Community Group on speeding in Parish | 1) Plan to recruit volunteers to help with installation 2) May need more consultation | No | Purchase and installation More consultation Continue to liaise with Parish Community Group |  |
| 7 | Maintain and replace bus shelters Cllrs Dixon, Turner | All bus shelters surveyed and photographed | Generally structurally sound except Dun Horse shelter where the roof is failing and requires replacement. Park Lane waste bin is loose and needs re-fixing. All could benefit from a good clean and internal painting. Cut back of foliage would improve the presentation. Possibly fill in the sides (presumably once windows on some), but this does not appear to allow much, if any, water ingress. |  | Prepare and execute a maintenance programme based on the survey |  |
| No. | Project | Output | Comment | Any Problems? |  | Outstanding Action |
| 8 | Produce Information on walks in the Parish Cllr Hydes | 1) Obtained map of footpaths and bridleways in Parish 2) Downloaded 1 walk from HDC’s website 3) Obtained copies of Mannings Heath Millennium Committee walks | On track | No |  | (i) Find more walks (ii) put walks on the Parish Council website (iii) produce leaflets/pamphlet on walks |
| 9 | Improve the look of the Parish by maintaining and enhancing green spaces Cllrs Boulter, Court | 1) Continuing to monitor grass cutting |  |  |  | On-going. Review planned in Autumn for bulb planting |
| 10 | Modernise (green) lighting columns Cllr Court, Clerk | 10 lighting columns replaced | Making very good progress | No |  | 1) 3 columns still need replacing, will include on Nov 2017 budget agenda 2) 2 further columns to be replaced opposite Mannings Heath Village Hall and in Harriots Close |